## Slide 1
Helping Global Health Partnerships to increase their impact
Stop TB Partnership – McKinsey collaboration
Thursday, November 5, 2009
Pre-reading for Coordinating Board presentation
CONFIDENTIAL AND PROPRIETARY. Any use of this material without specific permission of McKinsey & Company is strictly prohibited.
McKinsey & Company

## Slide 2
Contents
1
Project overview
2
Global Drug Facility
3
Advocacy
4
Communication, Marketing and Branding
5
Challenge Facility for Civil Society
6
MDR-TB Working Group
7
Next steps
Stop TB Partnership – McKinsey collaboration | November 2009
2

## Slide 3
The performance of Global Health Partnerships is increasingly important and scrutinized, yet achieving high performance is proving challenging
Increasing role of GHP performance
GHPs play a major role in global health
Performance of GHPs can have huge impact on the health of the world's population
The focus on performance is increasing, driven by
  Increasing donor focus on impact, effectiveness, and efficiency
  Increasing number of Partnerships in global health
  Likelihood of lower funding growth or less funding, given the financial crisis
Challenging factors
Complex environment and nature of GHP organizations create challenges, e.g.
Objective-setting: distinguishing between the change a GHP hopes to bring about in the world vs. the goals it sets itself that will help bring about the change
Accountability: ensuring accountability and delivery in the context of loose Partnership structures, voluntary membership, and limited hierarchy
Capabilities: gaining the capacity and capabilities needed to continuously improve performance
Source: McKinsey analysis.
3

## Slide 4
The project will deliver practical insights on improving GHP performance based on piloted improvement ideas
Goals
Develop a joint perspective, tested and proven, on how GHPs can improve performance, by
  Exploring how to improve performance in a GHP, not simply adopting existing (e.g., private-sector) approaches
  Testing new ways of working with Stop TB bodies that could lead to higher performance
  Developing a joint perspective to share with the global health community
Approach
Build on strengths and improvement opportunities outlined in the 2008 evaluation
Joint working, collaborative, co-creation — not client–consultant work
Duration ~22 weeks: 10 weeks diagnosis and design, 12 weeks delivery
Scope: 5 Partnership bodies — GDF, MDR-TB WG, CFCS, Advocacy, and CM&B teams
External interactions with other GHPs, e.g., RBM, UNAIDS, GAVI, GF
3 main end-products
Successful performance-improvement pilots in selected Partnership bodies, with documentation to support roll-out to other bodies
A co-authored project report, suitable for publication in major journals, detailing the experience and lessons for other GHPs
A “practitioner's guide” to support McKinsey teams conducting similar work
Source: McKinsey analysis.
4

## Slide 5
This project is organized in three distinct phases
Diagnose (August – September)
Selection of Partnership Bodies to work with — GDF, Advocacy, Communication/Marketing & Branding, CFCS, MDR-TB Working Group
Understanding of current performance
Identification of areas of high performance
Selection of one performance issue to improve
Design (September – October)
Intensive work within selected Partnership Bodies to develop improvement ideas on the selected performance issue
Select actions to implement in the next phase
Development of implementation plans for the Delivery phase
Deliver (November – December)
Implementation and refinement
Problem-solving sessions on findings, lessons learned, and implications
Workshop to share achievements across the Partnership
Report and publication of results; present results to the Coordinating Board in March 2010
Today
Source: McKinsey analysis. “Today” sits at the start of the Deliver phase (November 2009).
5

## Slide 6
We think about performance in terms of both processes and enablers — (1) Processes
Performance management
1
Set objectives
2
Set targets
3
Establish clear metrics
4
Track & disseminate metrics
5
Review performance
6
Celebrate & act
Set objectives & targets (steps 1–2)
Set time-bound objectives that contribute to fulfilling the mission and vision
Set metrics that directly measure agreed objectives
Set additional metrics that cascade down from the key metric
Set quantitative targets for the metrics; translate these into operational plans and budgets
Establish & track metrics (steps 3–4)
Produce progress reports
Disseminate reports to team members and stakeholders at pre-aligned intervals
Review & act (steps 5–6)
Use reports to discuss progress in structured review meetings
Identify possible performance gaps and decide how to address them
Celebrate successes and take any required corrective actions
Source: McKinsey analysis.
6

## Slide 7
Definition of performance management terms
Definition of performance management terms
Term | Definition / description | Example
Objective | Narrow, time-bound, quantifiable goal that contributes to delivering the mission | Supply low-cost, quality TB drugs at USD 20/treatment course for X patients in 2010
Metric | Measurable variable that indicates progress toward an objective | Funds raised; patient treatments supplied; grants approved
Target | The target value of the chosen metric | 15 million patient treatments supplied by 2010
Report | A set of metrics and current values vs. target, with reasons for performance | See dashboard examples in this document
Performance review | A sequence of meetings to review performance, find root causes, and agree actions | Quarterly team review meeting
Mission | Defines the organization's purpose and primary objectives | Supply low-cost, quality drugs to countries that need them
Vision | Articulates the aspiration or target for the future | A TB-free world
Source: McKinsey analysis.
7

## Slide 8
We think about performance in terms of both processes and enablers — (2) Enablers
Committed leadership
Strong leadership involvement and dedication.
Capacity
Ensure sufficient skills, infrastructure, and resources for performance.
Communications
Communicate both performance and the importance of discussing performance regularly to all stakeholders.
Culture
Develop shared cultural norms for performance (e.g., accountability, behaviors).
Source: McKinsey analysis.
8

## Slide 9
Many GHPs find some performance processes challenging given their complex environment and structure
Performance management
1
Set objectives
2
Set targets
3
Establish clear metrics
4
Track & disseminate metrics
5
Review performance
6
Celebrate & act
Setting objectives & targets
Getting from a vision to specific objectives for the partnership and its bodies, rather than directly to activities
Aligning divergent partner views on which objectives to pursue
Committing to targets is difficult because some targets are not entirely deliverable by the partnership, the voluntary nature of partnerships, and consequences of missing targets (e.g., future funding)
Metrics & data
Agreeing the right metrics for objectives that are difficult to measure, e.g., awareness about TB
Aligning organization structures with performance drivers and metrics to enable clear accountability
Getting good performance data given in-country data-gathering limitations
Advocacy specifics
Setting advocacy objectives that stay current and relevant in changing external circumstances
Finding and making visible tactical advocacy opportunities for partners
Source: Interviews with Stop TB Partnership, GAVI, and UNAIDS.
9

## Slide 10
Many GHPs also struggle with the right enablers
Committed leadership
Ensuring leaders regularly lead and participate in performance reviews, in spite of many other calls on their time.
Capacity
Allocating appropriate resources to performance management given limited resources for internal processes.
Communications
Establishing a shared understanding of accountability across the different backgrounds of partners; keeping partners in a loose working group engaged and motivated.
Culture
Moving from a culture of performance measurement (extensive reporting) to performance management (open discussion of outcomes); defining ambitious goals despite a consensus-building culture that tends toward abstract objectives.
Source: Interviews with Stop TB Partnership, GAVI, and UNAIDS.
10

## Slide 11
The Stop TB Partnership displays a number of strengths across performance processes
Strengths across performance processes
Setting objectives — GDF objectives are clearly defined and distinguish the change GDF hopes to bring about in the world (e.g., MDGs — 70% of TB cases diagnosed, 85% cure rate) from the internal goals it sets itself
Tracking and disseminating metrics — despite limited resources, GDF tracks and reports on a wide variety of metrics to meet the different demands of donors
Establishing clear metrics and setting targets — the MDR-TB Working Group defines concrete metrics (e.g., patients with access to MDR-TB treatment) and sets specific targets (e.g., for 2009: 200,000 patients, 4 projects)
Reviewing performance — the Advocacy Team conducts an in-depth review of performance against objectives stated in its funding proposal, taking stock of results and lessons learned
Source: McKinsey analysis; interviews.
11

## Slide 12
Brief overview of performance issues we jointly agreed to address across the five Partnership bodies
Performance issues agreed across the five Partnership bodies
Partnership body | Central GHP performance issue | Specific question addressed
GDF | Agreeing the right metrics for objectives that are difficult to measure | GDF tracks 250 metrics, but not all relate to GDF, some overlap, and metrics are not organized hierarchically
Advocacy | Setting advocacy objectives that stay current and relevant in changing external circumstances | Setting advocacy objectives within Stop TB that stay current; finding and making visible tactical opportunities
Comms, Marketing & Branding | Getting from a vision to specific objectives rather than directly to activities | Determining detailed objectives for each audience group and defining metrics for each
Challenge Facility for Civil Society | Getting from a vision to specific objectives rather than directly to activities | Refining the mission based on the first two years' experience and articulating specific objectives
MDR-TB Working Group | Agreeing the right metrics for objectives that are difficult to measure | Tying metrics explicitly to WG objectives; clarifying accountabilities and timelines
Source: McKinsey analysis.
12

## Slide 13
While most of the 250 metrics were relevant and helpful to GDF, data collection and reporting was onerous
“ All together we report on over 200 KPIs that cover our numerous external reporting requirements
“ Most individual KPIs are relevant and helpful
“ KPIs are specific and measurable
“ It is difficult to define metrics for some areas, so we have KPI gaps
“ Some of our KPIs overlap, so it is unclear what we are optimizing for
“ It takes too much time to collect the information and adapt it to our 200+ KPIs
“ Since the hierarchy of KPIs is not clear, it is hard to prioritize
Source: Interviews.
13

## Slide 14
The team followed an eight-step process to create streamlined, structured KPIs, dashboards, and review meetings
a Collate all GDF metrics reported on into one database: ~250 in total
b Agree on GDF objectives and cluster metrics/KPIs to objectives
c Develop a detailed KPI tree for each objective
d Streamline detailed trees, excluding activity-related or non-GDF-owned KPIs
e Assign owners to, and define review frequency of, each KPI
f Develop a clear cascade of KPIs from teams up to the COO annual performance review
g Create dashboards and review calendars for each team
h Hold a workshop on conducting performance dialogues
Source: McKinsey analysis.
14

## Slide 15
Seven KPIs give a clear overview of GDF's performance against its three main objectives
Seven KPIs map to GDF's three main objectives
# | Objective | KPI
1a | Provide uninterrupted supply of 1st- and 2nd-line TB drugs and diagnostics (low-cost, high-quality, timely, demand-driven, to eligible countries) | Number of patient treatments delivered
1b | (same objective) | Average cost per patient treatment
2a | Sustainably strengthen eligible countries' national drug management, procurement capacity, and financial self-sufficiency | Number of countries that move to direct procurement
3a | Ensure appropriate and efficient staffing and funding to drive the mission | Organizational health and culture index
3b | (same objective) | Staff capacity and capability index
3c | (same objective) | Funds raised vs. required for GDF administrative costs
3d | (same objective) | Funds raised vs. required for GDF activities
Source: McKinsey analysis; Annual GDF report 2008.
15

## Slide 16
The COO's annual dashboard tracks cost and volume against target across treatment lines
ILLUSTRATIVE — DUMMY NUMBERS
Average cost per patient treatment or diagnostic unit (USD), Actual vs. Target
Chart: 
| 1st line | Prophylaxis | 2nd line | Diagnostics
Actual | 4 | 4.1 | 2.1 | 2.5
Target | 3.8 | 3.5 | 1.9 | 1.9
Funds raised vs. required ($M)
Stream | Raised (X) | Required (Y)
GDF activities | 12.0 | 11.0
GDF administration | 2.1 | 1.7
Source: McKinsey analysis. Dummy numbers for illustration.
16

## Slide 17
Next steps to implement and capture benefits at GDF
Next steps to implement and capture benefits at GDF
Action | Description
Share KPI trees with donors | Present the GDF KPI tree to donors, compare with metrics they request, and agree on any additional KPIs to report
Integrate KPIs into MIS | Establish simple mechanisms within GDF's existing MIS to input and analyze the data required for KPIs
Complete performance-dialogue workshop | Run a two-hour workshop with GDF team leads on facilitating constructive performance dialogues
Embed KPIs in team performance review | Assign reporting responsibilities, schedule review meetings, complete one round of reviews, and refine based on feedback
Source: McKinsey analysis.
17

## Slide 18
Three steps ensure that emerging opportunities are incorporated into advocacy partners' plans and the Framework Document
Step I
Develop the sunflower — Get more information
Make advocacy every partner's business and increase information sharing
Extend the reach of TB advocacy beyond the Partnership
Step II
Filter the intelligence — Filter the information received
Set up a process that filters information for validity, impact, global relevance, and feasibility
Step III
Keep the framework relevant — Create or adjust objectives and plans
For tactical opportunities requiring immediate action, create new or adjusted objectives and define what success looks like
For all other opportunities, draft adjustments into the Framework Document and seek advice from the AAC
Source: Workshops.
18

## Slide 19
Information from an active, extended network is filtered across four criteria
PRELIMINARY
Validity
The received information is checked for validity with a second source: “Is the information accurate and true?”
Global
The information is filtered for global relevance: “Does it have implications beyond local/national boundaries?”
Impact
Once validated, the information is filtered for work-plan impact: can it affect policy, donors, or public opinion?
Feasibility
Determine whether the information can feasibly and realistically be translated into sufficiently impactful activities.
Unfiltered information in →
→ Filtered intelligence out
Source: Workshops. Apply the filter at the start of advocacy meetings.
19

## Slide 20
High-level objectives relate to three areas — raising awareness, engaging TB networks, and supporting the Secretariat
Mission: Inspire the world into action against tuberculosis (TB)
Objective 1 — Raise awareness about TB among:
A — The “fourth estate” (news media)
B — Members of the public in donor countries and selected high-burden countries / BRIC+2
C — Selected institutions
Objective 2 — Engage TB networks
Engage, support, and foster a shared sense of purpose among partners and other members of TB networks.
Objective 3 — Support the Secretariat
Provide coordinated support for the core work of the Secretariat.
Note: BRIC+2 = Brazil, Russia, India, China, Indonesia, and South Africa. Source: Team discussion.
20

## Slide 21
For each high-level objective, audience groups, objectives, metrics, and targets have been defined
Audience groups, objectives, metrics, and targets by high-level objective
Audience group | Objective | Metric | Target
Students & adults, donor countries | Raise awareness of the prevalence and threat of TB via traditional and innovative channels to grow donations | Total people reached through marketing channels | Online viral campaign: 30 million
Students & adults, high-burden countries | Develop and roll out a viral marketing / social-media campaign | People reached via social channels (YouTube, Facebook) | Social channels: 5 million
General public | (awareness) | % of population 18–65 acknowledging TB as a top-5 global health priority | TV PSAs: 5M; Internet PSAs: 10M
News media (fourth estate) | Meet with editors to encourage TB coverage; pitch high-impact topics (MDR/XDR-TB) | Number of editors engaged in ongoing dialogue | (target TBD)
Source: Team discussion.
21

## Slide 22
The team clarified the CFCS mission and defined objectives to deliver it
Mission: To provide support to community-based organizations engaged in advocacy and social-mobilization activities seeking to raise awareness and empower communities to become part of the solution in the fight against TB.
Assist community-based civil-society organizations
Provide small grants for projects that increase awareness and active participation of local communities and build their capabilities
Provide coaching and technical assistance to grant recipients
Strengthen links between grant recipients and local authorities
Bring organizations together to exchange best practices
Efficiently manage CFCS resources
Identify and stimulate high-quality, competitive applications
Develop selection criteria that ensure involvement of local health services and strengthen local autonomy
Hold grantees accountable to project milestones
Use simple evaluation processes that assess impact and integrate lessons learned
Source: McKinsey analysis.
22

## Slide 23
A team “barometer” survey assesses working-group engagement across four dimensions
Objectives and direction
The objectives of the WG are clear and members are fully aligned on them
The WG's leaders provide clear strategic direction
Delivery against objectives
I believe the WG is making good progress toward achieving its objectives
The WG is having a meaningful impact in the fight against MDR-TB
Individual contributions
My subgroup meaningfully contributes to the overall objectives of the WG
After meetings, accountabilities and deadlines for specific actions are clear
Mindsets & behaviors
The culture within the WG is collaborative and constructive
Members are encouraged to voice their opinions, even if controversial
Scale: 1 = strongly disagree … 5 = strongly agree.
23

## Slide 24
The next ~10 weeks will focus on implementing the solutions developed
Diagnose Aug – Sep
Design Sep – Oct
Deliver Nov – Dec
Today
Deliver-phase actions
Implementation within project teams begins
Problem-solving sessions on findings, lessons learned, and implications are conducted
Workshops to share achievements with other Partnership bodies are conducted
The report is produced and findings are published
Progress is presented to the Coordinating Board in March 2010
Source: McKinsey analysis.
24